## Clients
Client ID | Client Name | Industry | HQ Location | Client Since | Tier | Primary Contact | Account Lead | Annual Contract Value (USD)
CL-1004 | Atlas Manufacturing Co. | Manufacturing | Cedar Rapids, IA | 2019-03-11 | Strategic | Marguerite Doyle, COO | Priya Natarajan | 1450000
CL-1018 | NovaHealth Systems | Healthcare & Life Sciences | Minneapolis, MN | 2021-07-22 | Strategic | Dr. Felix Amato, CIO | Samuel Kestrel | 2100000
CL-1027 | Brightline Retail Group | Retail & Consumer Goods | Portland, OR | 2020-01-15 | Growth | Janelle Ruiz, VP Operations | Priya Natarajan | 680000
CL-1033 | Helios Energy Partners | Energy & Utilities | Calgary, AB | 2022-09-05 | Strategic | Owen Bracewell, VP Digital | Samuel Kestrel | 1825000
CL-1041 | Meridian Trust Bank | Financial Services | Charlotte, NC | 2023-02-14 | Growth | Linda Okwu, Director of Ops Risk | Tobias Lindqvist | 940000
CL-1052 | City of Beaumont Public Works | Public Sector | Beaumont, TX | 2023-11-30 | Standard | Carl Whitfield, Deputy Director | Tobias Lindqvist | 310000

## Projects
Project ID | Project Name | Client ID | Service Line | Engagement Lead | Start Date | End Date | Status | Budget (USD) | Actual Cost (USD)
PRJ-2201 | Atlas MFG — Plant Floor Digitization (Phase 1) | CL-1004 | Operations Excellence | Priya Natarajan | 2022-02-01 | 2022-11-18 | Completed | 1180000 | 1244500
PRJ-2309 | Atlas MFG — Plant Floor Digitization (Phase 2: Predictive Maintenance) | CL-1004 | Digital & Analytics | Priya Natarajan | 2023-09-05 | 2024-06-30 | Completed | 905000 | 873200
PRJ-2245 | NovaHealth — Clinical Data Interoperability Program | CL-1018 | Digital & Analytics | Samuel Kestrel | 2022-08-15 | 2023-12-20 | Completed | 2650000 | 2811000
PRJ-2401 | NovaHealth — Patient Scheduling Optimization | CL-1018 | Operations Excellence | Samuel Kestrel | 2024-01-08 | 2024-10-04 | Completed | 760000 | 742300
PRJ-2318 | Brightline Retail — Supply Chain Resilience Assessment | CL-1027 | Operations Excellence | Priya Natarajan | 2023-03-20 | 2023-08-11 | Completed | 410000 | 398750
PRJ-2412 | Brightline Retail — Store Replenishment Forecasting Pilot | CL-1027 | Digital & Analytics | Hana Brennan-Cole | 2024-04-01 | 2025-01-17 | Completed | 525000 | 561900
PRJ-2355 | Helios Energy — Grid Asset Digital Twin Roadmap | CL-1033 | Digital & Analytics | Samuel Kestrel | 2023-10-02 | 2024-03-29 | Completed | 690000 | 705400
PRJ-2501 | Helios Energy — Digital Transformation Phase 2 (Field Operations Platform) | CL-1033 | Digital & Analytics | Samuel Kestrel | 2025-02-10 | 2026-04-30 | In Progress | 2150000 | 1390000
PRJ-2444 | Meridian Trust Bank — Operational Risk Controls Uplift | CL-1041 | Risk & Compliance | Tobias Lindqvist | 2024-02-19 | 2024-12-13 | Completed | 870000 | 911200
PRJ-2509 | City of Beaumont — Public Works Asset Management Modernization | CL-1052 | Operations Excellence | Tobias Lindqvist | 2025-01-06 | 2025-12-19 | In Progress | 295000 | 168400

## Milestones
Milestone ID | Project ID | Milestone Name | Target/Actual Date | Status
MS-0001 | PRJ-2201 | Kickoff & Discovery Complete | 2022-02-24 | Complete
MS-0002 | PRJ-2201 | Current-State Assessment Signed Off | 2022-04-05 | Complete
MS-0003 | PRJ-2201 | Future-State Design Approved | 2022-05-28 | Complete
MS-0004 | PRJ-2201 | Pilot / MVP Go-Live | 2022-07-30 | Complete
MS-0005 | PRJ-2201 | Stakeholder Steering Committee Review | 2022-09-06 | Complete
MS-0006 | PRJ-2201 | Full Rollout Complete | 2022-10-25 | Complete
MS-0007 | PRJ-2201 | Hypercare & Closeout | 2022-11-18 | Complete
MS-0008 | PRJ-2309 | Kickoff & Discovery Complete | 2023-09-28 | Complete
MS-0009 | PRJ-2309 | Current-State Assessment Signed Off | 2023-11-09 | Complete
MS-0010 | PRJ-2309 | Future-State Design Approved | 2024-01-02 | Complete
MS-0011 | PRJ-2309 | Pilot / MVP Go-Live | 2024-03-08 | Complete
MS-0012 | PRJ-2309 | Stakeholder Steering Committee Review | 2024-04-16 | Complete
MS-0013 | PRJ-2309 | Full Rollout Complete | 2024-06-06 | Complete
MS-0014 | PRJ-2309 | Hypercare & Closeout | 2024-06-30 | Complete
MS-0015 | PRJ-2245 | Kickoff & Discovery Complete | 2022-09-23 | Complete
MS-0016 | PRJ-2245 | Current-State Assessment Signed Off | 2022-12-01 | Complete
MS-0017 | PRJ-2245 | Future-State Design Approved | 2023-02-27 | Complete
MS-0018 | PRJ-2245 | Pilot / MVP Go-Live | 2023-06-16 | Complete
MS-0019 | PRJ-2245 | Stakeholder Steering Committee Review | 2023-08-19 | Complete
MS-0020 | PRJ-2245 | Full Rollout Complete | 2023-11-10 | Complete
MS-0021 | PRJ-2245 | Hypercare & Closeout | 2023-12-20 | Complete
MS-0022 | PRJ-2401 | Kickoff & Discovery Complete | 2024-01-29 | Complete
MS-0023 | PRJ-2401 | Current-State Assessment Signed Off | 2024-03-07 | Complete
MS-0024 | PRJ-2401 | Future-State Design Approved | 2024-04-25 | Complete
MS-0025 | PRJ-2401 | Pilot / MVP Go-Live | 2024-06-23 | Complete
MS-0026 | PRJ-2401 | Stakeholder Steering Committee Review | 2024-07-28 | Complete
MS-0027 | PRJ-2401 | Full Rollout Complete | 2024-09-12 | Complete
MS-0028 | PRJ-2401 | Hypercare & Closeout | 2024-10-04 | Complete
MS-0029 | PRJ-2318 | Kickoff & Discovery Complete | 2023-03-31 | Complete
MS-0030 | PRJ-2318 | Current-State Assessment Signed Off | 2023-04-20 | Complete
MS-0031 | PRJ-2318 | Future-State Design Approved | 2023-05-16 | Complete
MS-0032 | PRJ-2318 | Pilot / MVP Go-Live | 2023-06-17 | Complete
MS-0033 | PRJ-2318 | Stakeholder Steering Committee Review | 2023-07-06 | Complete
MS-0034 | PRJ-2318 | Full Rollout Complete | 2023-07-30 | Complete
MS-0035 | PRJ-2318 | Hypercare & Closeout | 2023-08-11 | Complete
MS-0036 | PRJ-2412 | Kickoff & Discovery Complete | 2024-04-24 | Complete
MS-0037 | PRJ-2412 | Current-State Assessment Signed Off | 2024-06-04 | Complete
MS-0038 | PRJ-2412 | Future-State Design Approved | 2024-07-26 | Complete
MS-0039 | PRJ-2412 | Pilot / MVP Go-Live | 2024-09-28 | Complete
MS-0040 | PRJ-2412 | Stakeholder Steering Committee Review | 2024-11-05 | Complete
MS-0041 | PRJ-2412 | Full Rollout Complete | 2024-12-24 | Complete
MS-0042 | PRJ-2412 | Hypercare & Closeout | 2025-01-17 | Complete
MS-0043 | PRJ-2355 | Kickoff & Discovery Complete | 2023-10-16 | Complete
MS-0044 | PRJ-2355 | Current-State Assessment Signed Off | 2023-11-10 | Complete
MS-0045 | PRJ-2355 | Future-State Design Approved | 2023-12-12 | Complete
MS-0046 | PRJ-2355 | Pilot / MVP Go-Live | 2024-01-20 | Complete
MS-0047 | PRJ-2355 | Stakeholder Steering Committee Review | 2024-02-13 | Complete
MS-0048 | PRJ-2355 | Full Rollout Complete | 2024-03-14 | Complete
MS-0049 | PRJ-2355 | Hypercare & Closeout | 2024-03-29 | Complete
MS-0050 | PRJ-2501 | Kickoff & Discovery Complete | 2025-03-17 | Complete
MS-0051 | PRJ-2501 | Current-State Assessment Signed Off | 2025-05-18 | Complete
MS-0052 | PRJ-2501 | Future-State Design Approved | 2025-08-06 | Complete
MS-0053 | PRJ-2501 | Pilot / MVP Go-Live | 2025-11-12 | Complete
MS-0054 | PRJ-2501 | Stakeholder Steering Committee Review | 2026-01-09 | Complete
MS-0055 | PRJ-2501 | Full Rollout Complete | 2026-03-25 | Complete
MS-0056 | PRJ-2501 | Hypercare & Closeout | 2026-04-30 | Complete
MS-0057 | PRJ-2444 | Kickoff & Discovery Complete | 2024-03-13 | Complete
MS-0058 | PRJ-2444 | Current-State Assessment Signed Off | 2024-04-24 | Complete
MS-0059 | PRJ-2444 | Future-State Design Approved | 2024-06-17 | Complete
MS-0060 | PRJ-2444 | Pilot / MVP Go-Live | 2024-08-21 | Complete
MS-0061 | PRJ-2444 | Stakeholder Steering Committee Review | 2024-09-29 | Complete
MS-0062 | PRJ-2444 | Full Rollout Complete | 2024-11-19 | Complete
MS-0063 | PRJ-2444 | Hypercare & Closeout | 2024-12-13 | Complete
MS-0064 | PRJ-2509 | Kickoff & Discovery Complete | 2025-02-02 | Complete
MS-0065 | PRJ-2509 | Current-State Assessment Signed Off | 2025-03-23 | Complete
MS-0066 | PRJ-2509 | Future-State Design Approved | 2025-05-24 | Complete
MS-0067 | PRJ-2509 | Pilot / MVP Go-Live | 2025-08-09 | Complete
MS-0068 | PRJ-2509 | Stakeholder Steering Committee Review | 2025-09-23 | Complete
MS-0069 | PRJ-2509 | Full Rollout Complete | 2025-11-21 | Complete
MS-0070 | PRJ-2509 | Hypercare & Closeout | 2025-12-19 | Complete

## Charts - Budget vs Actual
Project ID | Budget (USD) | Actual Cost (USD)
PRJ-2201 | 1180000 | 1244500
PRJ-2309 | 905000 | 873200
PRJ-2245 | 2650000 | 2811000
PRJ-2401 | 760000 | 742300
PRJ-2318 | 410000 | 398750
PRJ-2412 | 525000 | 561900
PRJ-2355 | 690000 | 705400
PRJ-2501 | 2150000 | 1390000
PRJ-2444 | 870000 | 911200
PRJ-2509 | 295000 | 168400