## Risk Register
Risk ID | Project ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Mitigation Owner | Mitigation Plan | Status
RSK-001 | PRJ-2501 | Field technician adoption of new mobile platform lower than expected, slowing rollout | Adoption | 4 | 4 | 16 | Samuel Kestrel | Phased rollout with regional champions; in-field coaching during first 30 days post-go-live | Open
RSK-002 | PRJ-2501 | Integration with Helios legacy SCADA system delayed due to vendor API limitations | Technical | 3 | 5 | 15 | Hana Brennan-Cole | Engage SCADA vendor early; build middleware abstraction layer as contingency | Open
RSK-003 | PRJ-2444 | Regulatory examination timeline shifts, compressing remediation window | Regulatory | 3 | 4 | 12 | Grant Oyelaran | Maintain weekly sync with Meridian compliance office; pre-stage evidence packages | Closed
RSK-004 | PRJ-2245 | Data quality issues in legacy EHR extracts compromise interoperability mapping accuracy | Data Quality | 4 | 4 | 16 | Samuel Kestrel | Implement automated data profiling and exception triage workflow prior to mapping | Closed
RSK-005 | PRJ-2412 | Forecasting model overfits to pilot store seasonality, reducing generalizability | Technical | 3 | 3 | 9 | Hana Brennan-Cole | Cross-validate across non-pilot store clusters; add holdout regions | Closed
RSK-006 | PRJ-2509 | Public sector procurement freeze risk tied to municipal budget cycle (Q4 city council vote) | Commercial | 2 | 5 | 10 | Tobias Lindqvist | Secure multi-year purchase order ahead of fiscal year vote; maintain contingency scope reduction plan | Open
RSK-007 | PRJ-2309 | Sensor hardware lead times extend predictive maintenance pilot timeline | Schedule | 3 | 3 | 9 | Priya Natarajan | Pre-order critical sensor SKUs; identify secondary supplier | Closed
RSK-008 | PRJ-2401 | Clinical staff scheduling preferences conflict with optimization model recommendations | Adoption | 3 | 3 | 9 | Samuel Kestrel | Co-design constraint rules with charge nurses; allow manual override with audit trail | Closed
RSK-009 | PRJ-2501 | Currency exposure (CAD/USD) on multi-year fixed-price contract | Financial | 2 | 3 | 6 | Naomi Tran | Forward contract hedge for 60% of remaining CAD-denominated spend | Open
RSK-010 | PRJ-2444 | Key client stakeholder (sponsor) departure mid-engagement | Relationship | 2 | 4 | 8 | Tobias Lindqvist | Identify and brief secondary executive sponsor early in engagement | Closed